## Team Backlog (Moving Car)
# | Task Name | Assignee | Task Status | Expected time to finish | Actual time to finish
1 | Modifying Tasks.c | Ibrahim Mostafa | Done | 2023-07-15 | 2023-07-16
2 | Modifying FreeRTOSConfig.h | Ibrahim Mostafa | Done | 2023-07-15 | 2023-07-15
3 | Tasks creation | Mustapha Mohamed | Done | 2023-07-14 | 2023-07-15
4 | Vrifying system implementation analytical | Mohab Ahmed | Done | 2023-07-15 | 2023-07-16
5 | verifying system emplementation using SimSo | Mohab Ahmed | Done | 2023-07-15 | 2023-07-16
6 | verifing system implementation using Keil | Mustapha Mohamed | Done | 2023-07-15 | 2023-07-16
7
8

## Data Validation Range (hidden)
Task Status
To Do
Doing
Done